## Resource Plan
Source	XTIVIA Role	Bosch Category	#weeks	Utilization %	#hours/week	#estimated hours	Billing rate	Estimated billing amount
XTIVIA USA	Enterprise Liferay Architect	SWE4	12	100%	40	480	$138.00	$66,240.00
XTIVIA USA	Sr. Liferay/JavaScript Developer 2	SWE3	3	100%	40	120	$130.00	$15,600.00
XTIVIA India	Sr Liferay Portal/Java Developer	SWE3	12	100%	40	480	$42.00	$20,160.00
	Development Total					1080		$102,000.00

Source	XTIVIA Role	Bosch Category	#weeks	Utilization %	#hours/week	#estimated hours	Billing rate	Estimated billing amount
XTIVIA USA	Enterprise Liferay Architect	SWE4	15	100%	40	600	$138.00	$82,800.00
XTIVIA USA	Sr. Liferay/JavaScript Developer 2	SWE3	3	100%	40	120	$130.00	$15,600.00
	Development Total					720		$98,400.00

## LR Sizing
Feature Group	Tasks	Expected Case (days)	Hours		Notes
1	Total	135.07	1080.54	1.5525
1	Project management, scrum and other technical meetings	20.01	160.08	20%
1	System Testing/Bug Fixes	15.01	120.06	15%
1	Unexpected/unestimated tasks	13.05	104.40	15%
1	Features	87.00	696.00
1	Sprint "0" & Common Tasks			8.00
	Developer orientation & Developer laptop environment setup	2.00			1 day per xtivia developer
	Deep dive walkthrough of the requirements	1.00
	Solidify architectural approach	1.00
	Refine Kanban board to track development	1.00
	Set up project skeletons and code repos for custom widgets/modules	2.00			Includes source control rep setup and build file
	Create sales library site	1.00
	UX/UI Design: HTML Mockups for new screens	0.00			Bosch will create/provide the designs
1	Liferay Theme			5.00
	Update Bosch Auto Parts theme to handle logged-in users	5.00
1	Sales Library Portal			68.00
2	Login			15.00
	Set up connectivity/integration with Bosch CI-AM	5.00
	Create the autologin hook	5.00
	Integration testing and issue resolution	5.00
2	Home page after login			5.00
	Main landing page for logged-in users - content fragments	3.00
	Recently updated documents	2.00			Use an Asset Publisher to pull the 10 most recently updated documents and display them in a list using a simple display template
2	Document Library			31.00
	Display a list of folders	4.00
	Search by document type, product associations using Liferay categories	3.00
	Display a list of documents	5.00			Handles displaying a list of documents in a folder as well as search results
	Display category-based filters for doc type and product associations	3.00
	Implement search results filtering by categories	3.00
	Display document details with document preview (when supported by Liferay ootb)	7.00
	Email document	3.00
	Download document	3.00
2	Personal Library			9.00
	Enable personal library for each sales library user	2.00
	Set up personal library template	2.00
	Personal library customizations	5.00			This is a placeholder estimate
2	Forms			3.00
	Basis forms setup and training	3.00
2	Miscellaneous			5.00
	Responsive Support	5.00
1	Release Finalization			6.00
	Production rollout planning and coordination	2.00
	Production rollout	2.00
	Post-production rollout hypercare/support	2.00
	Load testing	0.00			No load testing is planned

## Requirements
Requirements	Priority	Included in base estimates?	Yes
Sales Reps need to be able to access sales support files and documents through secure login.	Must-Have
Custom screen and menu options appear for this audience type.	Must-Have	Yes
Integrates with Bosch’s Single Sign-On network for login.	Must-Have	Yes
Reps can search documents by type, name, product associations, and keywords.	Must-Have	Yes
I can email the documents from the document library singularly.	Must-Have	Yes
I can download the documents individually from here.	Must-Have	Yes
Newly added assets appear in a list/carousel, by date added on the custom landing page after login	Must-Have	Yes
Ability to access the sales library website on desktop, laptop, tablet, and smartphone	Must-Have	Yes
I can upload documents to folders I create as well, that are only available to me.	Should-Have	Yes
Ability to use a form builder to create and edit forms using a drag-and-drop form builder with the ability to access form submissions via a spreadsheet type view.	Should-Have	Yes
Ability for a sales library user to favorite (aka bookmark) sales library files and access his/her favorites	Nice-to-have	No	Can be added at an additional cost; probably another ~5 man days
Ability for a sales library user to share personal files with other users	Nice-to-have	No	Can be added at an additional cost
Ability for sales library users to save files to folders for bulk zip download or later recall.	Nice-to-have	No	Can be added at an additional cost
A mobile app to access the sales library	Nice-to-have	No	Can be added at an additional cost

## Estimations
Tasks	Expected Case (days)	Hours		Notes
Project setup	1
Setup personas with roles/permissions	2
Navigation template changes for RBAC	1

OIDC – CIAM Integration	17

Setup keycloack client instance	2
Creating OIDC Filter and autologin modules.	3
Authentication Code flow Implementation	3
User creation/Role assignment	3
Access Token validation/ refreshtoken implementation.	3
Creating custom logic to assign roles to internals(AutoLoginFilter.)	3

Rest Apis	15
Creating rest API endpoints to serve the data to the widget	2
Search document by name	2
Search document by type	2
Filter documents by category	2
Recently added documents.
Get my documents

Recently Added assets component	5

HTML	15

Recently view documents Screen	3
Theme changes.	3
List all folders/Files screen.	3
Upload Documents for Sales Representatives.	3
Document details screen	3
Responsive UI for all screens	5

## LR Sizing _2
Feature Group	Tasks	Expected Case (days)	Hours		Notes
1	Total	131.96	1055.70	1.5525
1	Project management, scrum and other technical meetings	19.55	156.40	20%
1	System Testing/Bug Fixes	14.66	117.30	15%
1	Unexpected/unestimated tasks	12.75	102.00	15%
1	Features	85.00	680.00
1	Sprint "0" & Common Tasks			8.00
	Developer orientation & Developer laptop environment setup	2.00			1 day per xtivia developer
	Deep dive walkthrough of the requirements	1.00
	Solidify architectural approach	1.00
	Refine Kanban board to track development	1.00
	Set up project skeletons and code repos for custom widgets/modules	2.00			Includes source control rep setup and build file
	Create sales library site	1.00
	UX/UI Design: HTML Mockups for new screens	0.00			Bosch will create/provide the designs
1	Liferay Theme			5.00
	Update Bosch Auto Parts theme to handle logged-in users	5.00
1	Sales Library Portal			66.00
2	Login			15.00
	Set up connectivity/integration with Bosch CI-AM	5.00
	Create the openidconnect filter and autologin filter.	5.00
	Integration testing and issue resolution	5.00
2	Home page after login			5.00
	Main landing page for logged-in users - content fragments	3.00
	Recently updated documents – asset publisher	2.00			Use an Asset Publisher to pull the 10 most recently updated documents and display them in a list using a simple display template
2	Document Library – custom react widget (No OTB Hook)			29.00
	Display a list of folders (They dont want to list folders)	0.00
	Search by document type, product associations using Liferay categories	3.00
	Display a list of documents	5.00			Handles displaying a list of documents in a folder as well as search results
	Display category-based filters for doc type and product associations	3.00
	back end code (APIs to filter data in the widget)	5.00
	Implement search results filtering by categories/types and keyword	5.00
	Display document details with document preview (when supported by Liferay ootb)	5.00
	Email document(Mail to client)	1.00
	Download document	2.00
2	Personal Library			9.00
	Enable personal library for each sales library user	2.00
	Set up personal library template	2.00
	Personal library customizations	5.00			This is a placeholder estimate
2	Forms			3.00
	Basis forms setup and training	3.00
2	Miscellaneous			5.00
	Responsive Support (Primarily for ipad view)	5.00
1	Release Finalization			6.00
	Production rollout planning and coordination	2.00
	Production rollout	2.00
	Post-production rollout hypercare/support	2.00
	Load testing	0.00			No load testing is planned